## Slide 1: Weekly CHRISTUS Health Deloitte Build Team Status Report
fancyDate

## Slide 2
Topic | Status
Overall Week Updates: Access Issues or Roadblocks | Bridges: Bridges team closing 19 tickets this week with 4 still in the queue. Paul has been onboarded to the team this week and Ross is still working on getting Paul the “contractor desktop.” MyChart: Team worked on 16 tickets this week closing 2 of them. Coordinated with on-shore team and completed review of all 144 Nova Notes. Off-shore team has been assigned 57% of Nova notes build task to be completed by 9/26. Priyanka Bure ‘s last day on the MyChart team will be Sept 1st and we are in the process of letting Vanessa know Harshit will be moving to the MyChart team while we backfill his role on the SER team. Cogito: Cogito team continues to make progress across all of the various projects including the open 6 reports. See slide 6 for more information. Clarity: Clarity team continues to make progress across all of the various projects including the open 5 reports. See slide 5 for more information. SER: Team completed 178 SNOW tickets this week. Progress has been made on the Coding and Claim Edit workqueue as well for the week ~22 providers releasing ~$74k in revenue. CareLink: Robin completed 18 site creations along with EAF builds for each of the site and migrated them to PRD. Quality Assurance: Task capture has been completed for 10 out of 24 Test Scripts. Environment Control and Data Courier (EC-DC): Team migrated over 54 DC SNOW requests all the way through to PRD. he team successfully completed the POTF clean-up activity, reducing the count to fewer than 50. ​The team discussed the POTF CSV clean-up effort, which involves over 450 providers, with Jeevan and aims to complete it by the end of next week. Test Automation: Team is working of development and testing of new test scripts​.Working on development of 3 new production automations (Quality review, Hyland Indexer, Finance Infor)​. Team is working on cross departmental testing. Team had a discussion with Epic QA regarding cross departmental testing for inpatient workflows
On-boarding/Off-Boarding Additional Deloitte Support | Application Specific On-boarding Updates - Paul J will be supporting the Bridges team as of 8/18 Application Specific Off-boarding Updates Priyanka Bure’s last day will be 9/1 PTO/Upcoming PTO: August PTO’s: Paul J- 08/18 & 08/19 Priyanka Pravallika, Adari- 08/18 Balagopalan, Akhila - 08/18 t0 08/20 Tanuja, Sunkara- 08/28,08/29 Zalavadia, Parth - 08/28,08/29 Wedding PTOs (Tentative) Tanu – 8th to 24th of December Anusree – 15th to 19th December Priyanka Adari – 25th September to 3rd October (engagement) and 22nd October to 14th November (wedding)
Overall CHRISTUS / Deloitte Pod Engagement Status
> 2 Weeks of Work Packets
< 2 Weeks of Work Packets
< 3 Weeks of Work Packets
Legend
Notes: ·

## Slide 3
Week Ending shortDate - Work Packet Status Report
Item / Application | WP Pipeline Status | Overall Status | Outstanding Items / Upcoming Activities
EC Link | ● | Completed 14 site creations along with EAF & DEP builds for each of the site and migrated them to PRD. | Ticket Status: Completed – 14
SER | ● | SER Team worked on following imports:- Successfully imported 270 Student RNs Planning for NPPES load-2 imports CSV Blueprint imported Working on MD-Staff Epic integration testing Worked on 100 Duplicate providers Worked on Blueprint Activation Button document POTF and POTF CSV- 260 Providers were verified manually. SER team received and completed ~288 snow tickets. Workqueue Coding workqueue- Worked on 22 providers.($63.49K) Claim error workqueue- Worked on 31 providers($136,7K) | SER team will work on the NPPES load for 107700 providers Tx SER team will work on the NPPES load for 47000 providers LA SER team will work on NPPES load for 40000 providers NM and AR Meditech import for 24000 providers. SER Team giving On-Call support SER team will continue working on upcoming Service now including SER provisioning tickets and RTASK SER Team will continue working on provider on the fly (POTF, POTF CSV, and Deloitte All) RWB Ad-Hoc reports in which 500 providers are to be verified SER Team will continue working on inactivating and hiding duplicate provider SERs

## Slide 4
Week Ending shortDate - Work Packet Status Report
Item / Application | WP Pipeline Status | Overall Status | Outstanding Items / Upcoming Activities
MyChart | ● | Completed:REQ1757713, REQ1732465. REQ1759996, REQ1750184, RTASK0440330, REQ1745506, REQ1731558 REQ1712510, REQ1755157 CIM0061533: CMT: T100-122393 RTASK0440458: Following up with requestor REQ1751067: Created CMT- T100: 122896 REQ1756069:Follow up sent REQ1757930: CMT- T100: 123463 REQ1760731: Created RTASK REQ1761497: Created RTASK REQ1763406: Created RTASK REQ1763412: Created RTASK INC5005128: Email sent to requestor INC4982596; CMT: T100-123282 REQ1767880: Awaiting approval to disable open scheduling REQ1757906: Awaiting requestor response Nova Notes triple upgrade: Coordinated with on-shore team and completed review of all 144 Nova Notes. Off-shore team has been working on assigned 71% of Nova notes build task to be completed by 26th sept,2025 | Ticket Status: WIP- REQ: 11, INC: 02, CIM; 01, RTASK:01 Closed- 09 Routed- 00 On Hold: 00 MyChart Gold stars and Diamonds: Pre-Care: Symptom Checker & E-visit: Awaiting demo call to be rescheduled. MyChart Messaging for All: We will be discussing with Samanth on 9/23 Finance: Paperless billing: Received approval from Legal & Marketing team for communication letter. Call has been scheduled for 10/03 . Long-term Care: Hypertension Care Plan: Reviewing pending tasks in CMT before pursing Sub-Cab for movement to PRD. All other items to be reviewed with leadership. Receiving Care: MyChart Bedside: I discussed the education content with the ClinDoc Leadership and opened a ticket for their review. Multilingual in MyChart: The next step is to present to the Digital Steering Committee in September. Vanessa will take it from here
Bridges | ● | Team have 2 tickets in the queue. Shared resolutions and documented in the work packet. Nova Notes Feb/May/Aug 24 project: Started with Feb/May/Aug upgrade project for nova notes owning the complete review, build and deployment. Total we have 93 nova notes for review. RA2318 September SU upgrade: We have total 2 nova notes, and we have started reviewing them with Epic TS. | Ticket Status: •WIP- 1 INC •Closed- 15 INC, 1 ITASK, 1 RTASK, 1 CIM •Routed- 1 INC

## Slide 5
Week Ending shortDate - Work Packet Status Report
Item / Application | WP Pipeline Status | Overall Status | Outstanding Items / Upcoming Activities
Clarity | ● | Clarity Team is working on the below tasks - Healthy Planet – RW SQL report to run to check clinician postponing HM topics Epic User-Name crosswalk report. BD Health Site – Inventory Optimization. Convert RWB extracts to SSIS. Clarity: RWSQL report for referral WQ Report needed for stats for anesthesia chart closures Custom request/ CT exam report AMB clinic needs help with longterm prescription without pain agreement CHS Population health report request | REQ1343496 (Healthy Planet – RW SQL report to run to check clinician postponing HM topics) - In Progress: Sent email to Dr CS with list of groupers with department list for review. REQ1475577 (Epic Username crosswalk report) - Testing: Need to reach back to Natasha to review updates with her to determine if this report is good with recent updates. RTASK0331890 (BD Health Site – Inventory Optimization) - Testing: Got update from Mindy the extract looks good, team has call with BD healthsite team on friday for a working session, awaiting feedback. RTASK0411360: (Convert RWB extracts to SSIS) - In Progress: Reached out to Mindy regarding the criteria session, she mentioned that she will follow upon location criteria and let us know what needs to be included. REQ1709866: (Clarity: RWSQL report for referral WQ) – Pending customer : Awaiting user response to close the request. REQ1453128: (Report needed for stats for anesthesia chart closures) – Testing :Report has been moved to PRD for final review. REQ1508233: (Custom request/ CT exam report) – In progress : Had a connect with user to get some details around this request, started building the initial query. REQ1657115: (AMB clinic needs help with longterm prescription without pain agreement) – In progress :Created build in POC and will be performing testing REQ1664093: (CHS Population health report request ) – In progress :WIP

## Slide 6
Week Ending shortDate - Work Packet Status Report
Item / Application | WP Pipeline Status | Overall Status | Outstanding Items / Upcoming Activities
Cogito | ● | Cogito Team currently working on the below items: REQ1285475(Description Project): Working on changes requested by clients, Updating approved descriptions in TFS. REQ1338522 (Michael's SSRS Catalog Link Project)- 341/404 completed in POC, remaining 65 Awaiting owner's review. 285 Components moved to PRD. REQ1367147 (SA Parameter clean up) – 523/616 completed. Awaiting owner's review - 93 REQ1576770 (SSRS Combine Duplicate Folder): 09/12: Working on disabling of 17 Link components for Archived Reports (555/555). REQ1633458 – A slicer dicer session – 09/12: On Hold, Sherlock ticket has been raised by Monica and have reached out to Epic Support to assist as discussed with Monica , waiting for Epic Support's inputs. REQ1591464 (In Progress): CMT is being moved to PRD and awaiting end user feedback. REQ1574554: Mindy sent a mail to check the availability of end user to connect and get the requirements of the request. REQ1742463: (Completed)– Updated the Hyperlinks in the components and created CMT ticket to move to PRD. Closed the request as per the communication from Reann. | Actively following up with Owners for Branding and Description work review and feedback.. Analyzing, Following up with end user(customer) and Working on Backlog Requests which are pending from 2023 and 2024 of Sam's Queue Monitoring the Queue and Triaging the Tickets. REQ1574554 – Request for new graphing component Completed: 0 Received from Clarity: 0 Awaiting Owners review: 4 (Branding, Description & SA Parameter clean up task) Work in Progress: 9 Tickets
Report Status ____________________ Type of Work | Returned to Deloitte/ re-work | # of Reports WIP with Deloitte | # of Reports Pending for Owners review | # of Reports Ready to Deploy | # of Reports Deployed to PRD | # of Reports Out of Scope | Total # of Reports
SSRS Description Work | 0 | 0 | 3 | 251 | 189 | 173 | 616
SSRS Branding Work | 0 | 0 | 11 | 221 | 173 | 211 | 616
SSRS Epic Catalog Link Components | Completed Component build in POC | Completed Catalog Branding changes | Completed Catalog Description changes | Updated approved Descriptions in TFS reports in this week
Cumulative Count (Overall) | 355 | 405 | 440 | 440
Week Ending 09/26- Work Packet Status Report Count 05/9/2025 | - | - | - | -

## Slide 7
Week Ending 09/26- Work Packet Status Report 07/04 - Work Packet Status Report
Item / Application | WP Pipeline Status | Overall Status | Outstanding Items / Upcoming Activities
Quality Assurance | ● | As part of Converge Integration Testing: Completed Execution of 36 out of 40 Phase 1 assigned Testcases. 4 Test Cases from Phase 1 were Removed from execution as they involve Third Party Applications. Completed Execution of 42 Phase 2 Testcases. Completed Execution of 31 phase 3 testcases Completed 42 Manual Run time calculation test cases. Completed 44 Task Capture Testcases. Created 5 short scripts as part of Converge Integration testing suite. Completed Review of 28 Regression Review Testcases. Standardized Documentation Process. Completed the Re Task Capture for 4 Test Cases Completed execution of 9 scripts of Nov24 Upgrade Regression testing. Completed Execution of 6 Testcases from MD Staff Regression testing Completed Execution of 4 Testcases from CGSM Peds Therapy IWT Completed Manual Run Time for 24 Scripts Completed NLA Gastroenterology Testing Completed Task capture of 16 scripts out of 24. | Nov24 Upgrade Regression: Total assigned: 9 Completed: 9 In Progress: 0 Number of defects raised: 4 CGSM Peds Therapy IWT Total assigned: 4 Completed: 4 In Progress: 0 Number of defects raised: 1 Task capture- 1 Re -Task Capture-1 Manual Run time Total assigned: 24 Completed: 24 NLA Gastroenterology Testing: Total Assigned - 2 Completed – 2 Task Capture: Total Assigned: 24 Completed: 16 On Hold: 8
Test Automation | ● | Team has started the pre regression testing from Monday, September 15th Out of 50 test cases 26 have already passed in the pre regression testing Team had presented the automation idea on EAP (Epic all procedures) during the bi-weekly call on Wednesday Automation scrum call at 8:30PM IST every Tuesday and Thursday Deloitte + Internal RPA mandatory connect at 7:30Pm IST every Monday and optional connect on Wednesday Timecard submission at end of every Friday | Regression Testing period for triple upgrade is Sept 29 – Oct 10

## Slide 8
Item / Application | WP Pipeline Status | Overall Status | Outstanding Items / Upcoming Activities
Environment Control and Data Courier (EC-DC) | ● | CMT Audit Process Documentation: Developed a comprehensive document outlining the audit process for standard changes, including detailed steps, defined roles, and compliance requirements. Minor CMT Audit: Engaged in team discussions to establish the process for daily audits of minor changes moved to PRD. Provided feedback to enhance how audit analysis is communicated to the respective application team leadership. Duplicate Provider Cleanup: Reached the halfway mark in phase 1 of the duplicate provider cleanup, processing over 500 provider records to date. CIRT Documents Review: Facilitated a team review session to discuss and refine the high-level CIRT process document. DC Migration SNOW Requests: Resolved more than 60 DC Migration SNOW requests, successfully sending builds through to production. DC Provider Maintenance & SER Migration: The team ran the DC Provider maintenance report daily and migrated over 300 SER records from PRD to POC to TST throughout the week. Daily CMT Report & Standards Audit: Ensured the Daily CMT Report was executed, generated a report of Standard CMTs moved to PRD, and audited approximately 300 standards. Increased the daily audit rate of standard changes moved to PRD from 30% to 50%. EHR Sub-CAB QA Activities: Conducted quality assurance on 27 Minor, 4 Standard Candidate, 1 Emergency, and 1 Urgent CMTs and change requests for EHR Sub-CAB meetings this week | Continue phase 1 provider cleanup by reviewing and resolving remaining SER records.
Week Ending shortDate - Work Packet Status Report

## Slide 9
Chart: SER Utilized Hours
| Available Hours | Utilized Hours
 | 0 | 80
Chart: Cogito Utilized Hours
| Available Hours | Utilized Hours
 | 0 | 120
Chart: MyChart Utilized Hours
| Available Hours | Utilized Hours
 | 0 | 80
Chart: Bridges Utilized Hours
| Available Hours | Utilized Hours
 | 0 | 80
Chart: CareLink Utilized Hours
| Available Hours | Utilized Hours
 | 0 | 25
Chart: Clarity Utilized Hours
| Available Hours | Utilized Hours
 | 0 | 120
Week Ending shortDate - Work Packet Status Report

## Slide 10
Chart: QA Utilized Hours
| Available Hours | Utilized Hours
 | 0 | 80
Chart: EC-DC Utilized Hours
| Available Hours | Utilized Hours
 | 0 | 80
Chart: Test Automation Utilized Hours
| Avaliable Hours | Utilized Hours
Utilization | 0 | 100
Week Ending shortDate - Work Packet Status Report